|  |  |  |
| --- | --- | --- |
| APTlogogreen3 | ASIA-PACIFIC TELECOMMUNITY |  |
| **The APT Conference Preparatory Group for WRC-19**  |  |
|  |  |

**TENTATIVE WORKPLAN FOR THE PREPARATION OF RA-19 AND WRC-19 (Updated at APG19-2)**

| **Year** | **Date/venue** | **APT activities** | **ITU activities** | **APG Actions** |
| --- | --- | --- | --- | --- |
| 2016 | 26 – 28 July 2016 Chengdu,People’s Republic of China | The 1st Meeting APT Conference Preparatory Group Meeting for WRC-19 **(APG19-1)** |  | * Election of APG Chairman and Vice-Chairmen
* Setup APG structure
* Appointment of office bearers
* Adoption of the revised working methods of APG
* Adoption of tentative workplan for the preparation of RA-19 and WRC-19
 |
| September to November 2016(see details on [ITU webpage](http://www.itu.int/en/events/Pages/Calendar-Events.aspx?sector=ITU-R)) |  | 2nd round of ITU-R Study Groups Meetings | Follow up the results of ITU-R Study Groups and Working Parties and dispatch necessary information in APG email reflectors |
| 12 – 16 December 2016Geneva |  | **WRS-16** |  |
| 2017 | February to June 2017(see details on [ITU webpage](http://www.itu.int/en/events/Pages/Calendar-Events.aspx?sector=ITU-R)) |  | 1st round of ITU-R Study Groups Meetings | Follow up the results of ITU-R Study Groups, Working Parties and **TG 5/1** and dispatch necessary information in APG email reflectors |
| 25 – 27 April 2017Geneva |  | **RAG-24** | Follow up the results of RAG-24 and dispatch necessary information in APG email reflectors |
| 2017 | 17 – 21 July 2017Bali, Indonesia | The 2nd Meeting APT Conference Preparatory Group Meeting for WRC-19 **(APG19-2)** |  | * Consideration of the study results of ITU-R Study Groups
* Develop preliminary views on WRC-19 agenda items based on Members’ contributions
* Consideration of the outcomes of RAG-24 and take appropriate actions for the preparation of RA-19
* Develop preliminary view on RA-19 related issues based on members’ contributions, if any
* Assign WRC-19 agenda item coordinators in each Working Parties of APG
 |
| September to November 2017(see details on [ITU webpage](http://www.itu.int/en/events/Pages/Calendar-Events.aspx?sector=ITU-R)) |  | 2nd round of ITU-R Study Groups Meetings | Follow up the results of ITU-R Study Groups, working parties and **TG 5/1** and dispatch necessary information in APG email reflectors |
| 21 – 22 November 2017 (2 days)Geneva |  | **1st ITU Inter-regional Workshop on WRC-19 Prep.** | APT participation and preparation of contributions |
| 2018 | Mid-January to July 2018(see details on [ITU webpage](http://www.itu.int/en/events/Pages/Calendar-Events.aspx?sector=ITU-R)) |  | 1st round of ITU-R Study Groups Meetings | Follow up the results of ITU-R Study Groups, working parties and **TG 5/1** and dispatch necessary information in APG email reflectors |
| 2018 | 12 – 16 March 2018 (5 working days)Perth, Australia ***Note:***Two-day training workshop is planned on 9 and 10 March 2018, and briefing session for drafting group chairmen is planned on 11 March 2018  | The 3rd Meeting of APT Conference Preparatory Group for WRC-19 **(APG19-3)** |  | * Consideration of the study results of ITU-R Study Groups
* Update preliminary views on WRC-19 agenda items based on the outcomes of APG19-2 and members’ contribution
* Undertake an initial review of issues related to RA-19 activities and develop a timetable for the development of harmonised APT Views
* Development of any radiocommunication related proposals for PP-18 for the consideration of APT Preparatory Group for PP-18
 |
| 26 – 29 March 2018Geneva |  | **RAG-25** | Follow up the results of RAG-25 and dispatch necessary information in APG email reflectors |
| 17 – 27 April 2018Geneva |  | **Council 2018** |  |
| September to November 2018(see details on [ITU webpage](http://www.itu.int/en/events/Pages/Calendar-Events.aspx?sector=ITU-R))  |  | 2nd round of ITU-R Study Groups Meetings | Follow up the results of ITU-R Study Groups, working parties and **TG 5/1** and dispatch necessary information in APG email reflectors |
| [Q4, 2018]Normally near the end of the 2nd round of ITU‑R Study Groups Meetings and not in parallel with PP‑18 |  | **2nd ITU Inter-regional Workshop on WRC-19 Prep.** | APT participation and preparation of contributions |
| 29 October – 16 November 2018 Dubai, United Arab Emirates |  | **PP-18** | Follow up the outcomes of PP-18 related to radiocommunication and dispatch necessary information in APG email reflectors |
| 2019 | 7 – 12 January 2019(6 working days)Republic of Korea | The 4th Meeting of APT Conference Preparatory Group for WRC-19 **(APG19-4)** |  | * Finalise APT contributions to the CPM19-2
* Update preliminary views on WRC-19 agenda items
* Arrangements for coordination during CPM19-2
 |
| 18 – 28 February 2019Geneva | Coordination Meetings | **CPM19-2** | * Ensure that the APT’s contributions are well treated and reflected in the outcomes of CPM19-2
* Coordinate views with other regional organisations and take necessary actions to promote APT’s interests
* Follow up the results of CPM19-2 and dispatch necessary information in APG email reflectors
 |
| [April/May 2019] |  | **RAG-26** |  |
| 10 – 20 June 2019Geneva |  | **Council 2019** |  |
| 31 July – 6 August 2019 (6 working days, excluding 4 August)Japan | The 5th Meeting of APT Conference Preparatory Group for WRC-19 **(APG19-5)**  |  | * Finalise Preliminary APT Common Proposals for RA-19 and WRC-19
* Arrangements for coordination during RA-19 and WRC-19
 |
| [3 days in September 2019] |  | **3rd ITU Inter-regional Workshop on WRC-19 Prep.** | APT participation and preparation of contributions |
| 2019 | 21 – 25 October 2019Egypt | Coordination Meetings | **RA-19** | * Ensure that the APT’s contributions are well treated and reflected in the outcomes of RA-19
* Coordinate views with other regional organisations and take necessary actions to promote APT’s interests
* Follow up the results of RA-19 and dispatch necessary information in APG email reflectors
 |
| 28 October – 22 November 2019 Egypt | Coordination Meetings | **WRC-19** | * Ensure that the APT’s contributions are well treated and reflected in the outcomes of WRC-19
* Coordinate views with other regional organisations and take necessary actions to promote APT’s interests
* Follow up the results of WRC-19 and dispatch necessary information in APG email reflectors
 |
| 2020 | [Q2 or Q3 2020]Host to be decided | The 1st Meeting of APT Conference Preparatory Group for WRC-23 **(APG23-1)** |  | * New APG structure
* APG work plan and ToR
* Start preparation of APT preliminary views on WRC-23 agenda items
 |