|  | ASIA-PACIFIC TELECOMMUNITY |  |  |
| --- | --- | --- | --- |
|  | The 2nd Meeting of the SATRC Working Group on Policy and Regulation |
|  | 28 – 29 December 2011, New Delhi, India |  |  |

Document No.: SATRC-WG-PR-1/04

Date: 10 August 2010

workplan of the working group on policy and regulation

Introduction

The Working Group on Policy and Regulation was established in accordance with the decision taken at the 11th SATRC Meeting in Colombo, Sri Lanka from 24 – 26 November 2009 to implement Phase-III of the Action Plan for the duration of 2010-2011 to deal with the issues related to Policy and Regulation in the region. This WG is chaired by Telecommunications Regulatory Authority of India (TRAI).

In Working Group on Policy and Regulation, four Work Items as detailed below have been identified and all the member countries were urged to participate actively in these Working Group activities.

At the First Meeting of the WG, the WG developed it’s workplan on each assigned work items for the implementation period of SATRC Action Plan Phase III by consensus amongst the WG members. The workplan was developed based on the adopted Terms of Reference of WG adopted in consensus at the WG meeting (Document No. SATRC-WG-PR-1/05). The adopted workplan is as follows:

| Work Item | Facilitation of broadband in SATRC countries |
| --- | --- |
| Document Type | Report |
| Group/Chair | Bhutan |
| Editor(s) | Mr. Wangay Dorji |
| Scope | Review of previous study reports on the subject Collect the information on existing broadband scenario & bottlenecks in proliferating broadband in SATRC countries Identify regulatory and policy issues which may facilitate of broadband in SATRC countries. Study of International practices. Consider need and time for migration to IPv6. Develop best practice guidelines/recommendations specific to SATRC region. |
| Purpose | To provide guidance to administrations/regulators for increasing broadband penetration |
| Related Document | [ TBD] |
| Related Organization | SATRC |
| Timelines | Collection of country specific information, impediments and regulatory environment : by 15th September 2010 Preparation of interim reports/action plan : by 15th October 2010 Further study on identified issues and interim report : by 31st March 2011 Preparation of draft report : by 30th June 2011 Preparation of final report/recommendation: by 30th September 2011 |

| Work Item | VoIP Issues |
| --- | --- |
| Document Type | Guideline |
| Group/Chair | Sri Lanka |
| Editor(s) | Mr. M. C. M. Farook |
| Scope | Review of previous study reports Existing policy and regulations in SATRC countries regarding provisioning of VoIP services. Identify need for change in existing Regulatory and Policy issues. Study of International Practices. Explore various options to address the identified issues. Futuristic framework for VoIP services Preparation of report/recommendation |
| Purpose | To provide guideline pertaining to VoIP issues |
| Related Document | Previous report of the NGN WG, ITU, [ TBD] |
| Related Organization | SATRC |
| Timelines | Collection of country specific information and existing regulatory framework: by 15th September 2010 Preparation of interim report: by 15th October 2010 Futuristic regulatory framework for VoIP: by 15th December 2010 Consultation of the proposed framework: by 31st March 2011 Preparation of draft guideline: by 30th June 2011 Preparation of final guideline: by 30th September 2011 |

| Work Item | Adoption of green technologies and safety of wireless networks |
| --- | --- |
| Document Type | Report/Opinion/Guideline |
| Group/Chair | Nepal |
| Editor(s) | Mr. A. R. Khanal |
| Scope | Review the previous study reports. Collection of Information on contribution of telecom industry towards pollution and current developments in green technology deployment scenario in SATRC region. Alternative methods and strategies to encourage use of non-conventional sources of energy. Study on new technological break-through and International practices Information regarding existing threats and practices being adopted for Securing the wireless networks. |
| Purpose | To investigate the status of green telecom deployment and impact of EMF radiation |
| Related Document | Previous WG Report, ITU, [ TBD] |
| Related Organization | SATRC |
| Timelines | Country specific status of adoption of green telecom and security threat to wireless networks: by 15th September 2010 Preparation of interim report: by 15th October 2010 Further study on indentified issues: by 31st March 2011 Preparation of draft report: by 30th June 2011 Preparation of final report: by 30th September 2011 |

| Work Item | CIIP and Cyber Security |
| --- | --- |
| Document Type | Report/Opinion/Guideline |
| Group/Chair | India |
| Editor(s) | V. K. Agarwal |
| Scope | Review of previous study reports Information on Security levels of CIIP Collection of information regarding present threats and International practices in dealing with such threats. Existing international practices to secure IP network and related policy & regulatory issues. Develop a framework for cyber security & CIIP. |
| Purpose | Identification of key challenges for CIIP and cybersecurity |
| Related Document |  |
| Related Organization | SATRC |
| Timelines | Country specific information, initiatives for IP network protection and regulatory initiatives (Acts, Directives etc): by 15th September 2010 Preparation of Interim Reports: by 15th October 2010 Further study on identified issues and comments: by 31st March 2011 Workplan for protection of critical information infrastructure and cyber security: by 10th May 2011 Preparation of draft report: by 30th June 2011 Preparation of final report: by 30th September 2011 |

____________